## Overview
Project: | Through our own eyes
PROJECT TIMETABLE
|  | 2017 |  |  | 2018 | [11 empty] | 2019
|  | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Project activity
Kick-off preparation |  | 2017 10: All partners
Kick-off meeting |  | 2017 11: 29.11-2.12
Dissemination |  | 2017 12: Dissemination reports: every month
Database |  | 2017 12: Work Package 1: Database
Meeting in France |  | 2018 3: 15-17
Handbook |  | 2018 6: Work Package 2: Handbook
Meeting in Italy |  | 2018 12: 11
Course and Conference |  | 2018 12: Work Package 3: Course & Conferences
Course in Greece |  | 2019 3: 25-29
Conference (GR) |  | 2019 4: 12.4
Conference (IT)
Conference (TR)
Conference (FR)

## Work Packages
Project: | Through our own eyes
PROJECT TIMETABLE
|  | 2017 | 2018 | [11 empty] | 2019
|  | Oct-Dec | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Work Packages
Database |  | Create database | bar: 2018 1 to 2018 6
Report 1 |  |  | 2018 1: 15 artworks
Report 2 |  |  | 2018 3: 15 artworks
Report 3 |  |  | 2018 5: Corrections
Handbook |  |  | 2018 6: Create handbook
Report 4 |  |  | 2018 7: Write examples
Report 5 |  |  | 2018 9: Rewrite
Report 6 |  |  | 2018 11: Review
Training course |  |  | 2018 12: Course and conference
Report 7 |  |  | 2019 1: Prepare course; 2019 4: 12.4 (GR)
Report 8 |  |  | 2019 3: Course: 25-29.3
Report 9 |  |  | 2019 4: Prepare and implement conferences
Report 10 |  |  | 2019 7: Wrap-up
End |  |  | 2019 9: End

## Dissemination
Project: | Through our own eyes
PROJECT TIMETABLE
|  | 2017 | 2018 | [11 empty] | 2019
|  | Oct-Dec | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Dissemination
Report 1
Database |  | Work Package: Create Database | bar: 2018 1 to 2018 6
Report 2 | bar: 2018 1
Report 3 | bar: 2018 2
Report 4 | bar: 2018 3
Report 5 | bar: 2018 4
Report 6 | bar: 2018 5
Report 7 | bar: 2018 6
Handbook |  |  | 2018 6: Work Package: Create Handbook
Report 8 | bar: 2018 7
Report 9 | bar: 2018 8
Report 10 | bar: 2018 9
Report 11 | bar: 2018 10
Report 12 | bar: 2018 11
Report 13 | bar: 2018 12
Course and Conference |  |  | 2018 12: Work Package: Implement course and conferences
Report 14 | bar: 2019 1
Report 15 | bar: 2019 2
Report 16 |  |  | 2019 3: 25-29: course
Report 17 |  |  | 2019 4: 12.4 (GR)
Report 18 | bar: 2019 5
Report 19 | bar: 2019 6
Report 20 | bar: 2019 7
Report 21 | bar: 2019 8
End | bar: 2019 9